## Hoja1
TASKS | START DATE | DURATION | END DATE
Create a non functional UI | 2018-08-07 | 3 days -> 22 h | 2018-08-14
Make functional the UI | 2018-08-15 | 2 days -> 14 h | 2018-08-21
Create the logic for a standard set of data | 2018-08-22 | 3 days -> 22 h | 2018-08-29
Make dynamically the creation of elements using a given data | 2018-09-04 | 2 days -> 14 h | 2018-09-05
POSSIBLE DELAYS
Create a non functional UI
POSSIBLE ADVANCE OF THE WORK
Create the logic for a standard set of data
Problems encountered
The zoom of localhost
Change the size of the font when we minimaze
If there is a way of finishing the game before the timer, where do we go? To the game over or to the replay? | Button in the stats or under it
View the perfect machine in the replay??
Set the background to the screen size