## Hoja1
TASKS | START DATE | DURATION | END DATE
Create a non functional UI | 2018-08-07 | 3 days -> 22 h | 2018-08-14
Make functional the UI | 2018-08-15 | 2 days -> 14 h | 2018-08-21
Create the logic for a standard set of data | 2018-08-22 | 3 days -> 22 h | 2018-08-29
Make dynamically the creation of elements using a given data | 2018-09-04 | 2 days -> 14 h | 2018-09-05
POSSIBLE DELAYS
Create a non functional UI
POSSIBLE ADVANCE OF THE WORK
Create the logic for a standard set of data